## Sheet1
WHICH? | WHAT? | WHERE? | HOW? | FOUNDER | IMPORTANT | STATUS
BUG | Inverted setting for check box in SettingActivity. | SettingActivity |  | TrungDQ |  | DONE
FIX | Cõ chữ gramma in FullScreenSongDetail | FullScreenSong |  | HaiNNT
FIX | Chord view popup center. (tap on Chord Sign) | FullScreenSong |  | TrungDQ
FIX | Tách dòng change status | FullScreenSong |  | HaiNNT
BUG | Playlist after update NullPointerException. | Navigation Drawer |  | TrungDQ
BUG | Sometime got 2 main activities. | General | Press OK to Update > new activity comes | TrungDQ
FIX | Empty list notification (playlist, favorite, search result... and everywhere there is listview) | Listviews |  | HaiNNT
BUG | Cancel Auto Update no repeat. (HaiNNT) | MainActivity |  | HaiNNT
UPDATE | No more related song: notif user. (HaiNNT) | Song Detail Fragment |  | HaiNNT
UPDATE | Song Detail Fragment: minize? (HaiNNT) | Song Detail Fragment |  | HaiNNT
UPDATE | Add playlist button | Navigation Drawer |  | HaiNNT
BUG | Reselect dropdown item: recreate items | Search By Chord |  | HaiNNT
BUG | Add playlist in "Add to playlist" does not refresh list | Create playlist | Star Button > Add to playlist > Create playlist | HaiNNT
UPDATE | Author, Singer press to view more | Song Detail Fragment |  | HaiNNT
UPDATE | Zoom by fingers | FullScreenSong |  | HaiNNT
UPDATE | More controls to manage | FullScreenSong |  | HaiNNT
FIX | (All playlists will be deleted) Fix lanaguage… | LogoutActivity |  | HaiNNT
UPDATE | Synchronize request when logout | LogoutActivity |  | HaiNNT
BUG | Chord view position buttons | ChordViewFragment | Is up to device | HaiNNT
BUG | Add empty chord name > NullPointerException | Search By Chord |  | TrungDQ
FIX | Update checking timeout | SettingActivity |  | TrungDQ
BUG | Artist view song item click is not working | ArtistView |  | TrungDQ
BUG | Favorite in listviews star | Listviews |  | TrungDQ
``````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````````