## Sheet1
WHICH? | WHAT? | WHERE? | HOW? | FOUNDER | IMPORTANT | STATUS
BUG | Artist view song item click is not working | ArtistView |  | TrungDQ
BUG | Chord view position buttons | ChordViewFragment | Is up to device | HaiNNT
BUG | Add playlist in "Add to playlist" does not refresh list | Create playlist | Star Button > Add to playlist > Create playlist | HaiNNT
BUG | Sometime got 2 main activities. | General | Press OK to Update > new activity comes | TrungDQ
BUG | Favorite in listviews star | Listviews |  | TrungDQ
BUG | Cancel Auto Update no repeat. (HaiNNT) | MainActivity |  | HaiNNT
BUG | Playlist after update NullPointerException. | Navigation Drawer |  | TrungDQ
BUG | Reselect dropdown item: recreate items | Search By Chord |  | HaiNNT
BUG | Add empty chord name > NullPointerException | Search By Chord |  | TrungDQ
BUG | Inverted setting for check box in SettingActivity. | SettingActivity |  | TrungDQ |  | DONE
BUG | SQLite LIKE query with utf-8 > ORDER BY TITLE_ASCII | FavoriteFragment |  | HaiNNT
BUG | Search bar focus white background | General |  | TrungDQ
BUG | Logout > System exit | LogoutActivity |  | TrungDQ
BUG | Duplicate song list Favorite | FavoriteFragment |  | HaiNNT
BUG | java.lang.IllegalStateException: The content of the adapter has changed but ListView did not receive a notification. Make sure the content of your adapter is not modified from a background thread, but only from the UI thread. [in ListView(2131296325, class com.hqt.hac.helper.widget.InfinityListView) with Adapter(class android.widget.HeaderViewListAdapter)] at android.widget.ListView.layoutChildren(ListView.java:1585) at android.widget.AbsListView$CheckForTap.run(AbsListView.java:3006) at android.os.Handler.handleCallback(Handler.java:730) at android.os.Handler.dispatchMessage(Handler.java:92) at android.os.Looper.loop(Looper.java:213) at android.app.ActivityThread.main(ActivityThread.java:5225) at java.lang.reflect.Method.invokeNative(Native Method) at java.lang.reflect.Method.invoke(Method.java:525) at com.android.internal.os.ZygoteInit$MethodAndArgsCaller.run(ZygoteInit.java:741) at com.android.internal.os.ZygoteInit.main(ZygoteInit.java:557) at dalvik.system.NativeStart.main(Native Method) | ArtistView | Search for "ka", select Karic, do a very fast up and down scroll | TrungDQ
FIX | Cõ chữ gramma in FullScreenSongDetail | FullScreenSong |  | HaiNNT
FIX | Chord view popup center. (tap on Chord Sign) | FullScreenSong |  | TrungDQ
FIX | Tách dòng change status | FullScreenSong |  | HaiNNT
FIX | Empty list notification (playlist, favorite, search result... and everywhere there is listview) | Listviews |  | HaiNNT
FIX | (All playlists will be deleted) Fix lanaguage… | LogoutActivity |  | HaiNNT
FIX | Update checking timeout | SettingActivity |  | TrungDQ
FIX | Screen Orientation keep state | FullScreenSong |  | HaiNNT
FIX | Media player error notification more detail | MediaPlayer |  | HaiNNT
FIX | Cancel synching playlist. | SettingActivity |  | HaiNNT
FIX | Don't hide button of related songs | Song Detail Fragment |  | HaiNNT
FIX | Empty song list adapter | Listviews |  | HaiNNT
FIX | Avatar png icon black | Navigation Drawer
UPDATE | Zoom by fingers | FullScreenSong |  | HaiNNT
UPDATE | More controls to manage | FullScreenSong |  | HaiNNT
UPDATE | Synchronize request when logout | LogoutActivity |  | HaiNNT
UPDATE | Add playlist button | Navigation Drawer |  | HaiNNT
UPDATE | No more related song: notif user. | Song Detail Fragment |  | HaiNNT
UPDATE | Song Detail Fragment: minize? | Song Detail Fragment |  | HaiNNT
UPDATE | Author, Singer press to view more | Song Detail Fragment |  | HaiNNT
UPDATE | Empty playlist add "Add playlist" button | PlaylistManager |  | HaiNNT
FIX | Playlist highlight seleted item | Navigation Drawer